## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : KERALA
Annual Procurement Plan for Financial Year : |  |  |  |  | 2021-22
Date of Approval of Annual Procurement Plan : |  |  |  |  | 10-03-2021, 22-09-2021(Revision)
Approved By/Name of Approving Authority : |  |  |  |  | INSTITUTE MANAGING COMMITTEE, GOVT. ITI FOR WOMEN KALAMASSERY
S. No. | Procurement Category | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date | Remarks
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19]
1 | Minor Civil Works | GOVT. ITI FOR WOMEN KALAMASSERY | Library Reading Room and upgradation of Autocad Lab | 500000 | RA 1 | OPEN TENDER | STATE PROCUREMENT RULES | No | No | OPEN TENDER | National | 2021-04-16 |  | 2021-08-16 | 2021-07-01 | 1 | 2021-08-15
2 | Equipment, Furniture & other Goods | GOVT. ITI FOR WOMEN KALAMASSERY | LATEST NSQF TRADE SYLLABUS COMPLIANCE | 4790650 | RA 1 | GeM Procurement& RC procurement | STATE PROCUREMENT RULES | Yes | Yes | GeM Direct/ GeM L1/ GeM Bidding/ RC Purchase | National | 2021-04-16 |  | 2021-10-31 | 2021-04-30 | 7 | 2021-10-31
3 | Training of Teaching & Management Staff | GOVT. ITI FOR WOMEN KALAMASSERY | Training of Instructors and Management Staff | 120000 | RA 1 | OPEN TENDER | STATE PROCUREMENT RULES | No | No | OPEN TENDER | National | 2021-08-01 |  | 2021-11-30 | 2021-08-15 | 2 | 2021-11-30
4 | ICT Infrastructure | GOVT. ITI FOR WOMEN KALAMASSERY | Procurement of LCD interactive panels, Short throw projects etc for smart class room | 900000 | RA 1 | GeM Procurement | STATE PROCUREMENT RULES | Yes | Yes | GeM Direct/ GeM L1 | National | 2021-04-16 |  | 2021-09-30 | 2021-08-01 | 1 | 2021-10-31
5 | Purchase of Books & Other Learning Materials | GOVT. ITI FOR WOMEN KALAMASSERY | Purchase of NIMI Books for Book Bank | 100000 | RA 1 | Direct Purchase | STATE PROCUREMENT RULES | No | No | Direct Puchase from NIMI | National | 2021-04-16 |  | 2021-10-31 | 2021-07-15 | 1 | 2021-08-15
6 | Facilities for Trainees | GOVT. ITI FOR WOMEN KALAMASSERY | TA for OJT Trainees, Reading room Furniture | 189350 | RA 1 | RC procurement | STATE PROCUREMENT RULES | No | No | Direct R C Procurement | National | 2021-04-16 |  | 2021-10-31 | 2021-10-01 | 1 | 2021-11-15
#REF!
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refer to suggestive list mentioned in notes tab
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refer to suggestive list mentioned in notes tab

## Notes
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International